## WBS Project Plan
BENDING MACHINE IPC SOFTWARE – WBS PROJECT PLAN
Team: 2 × BE ¦ 1 × FE ¦ 1 × QA |  |  | Duration: 16 Weeks |  |  | Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD
WBS ID | Task / Deliverable | Owner | Days | Start (Week) | End (Week) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | Notes / Acceptance Criteria
LEGEND → |  | BE1 | BE2 | FE | QA | Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W1: ALL; Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W2: Gantt shading = task active in that week (use conditional formatting or review schedule)
1 | PROJECT MANAGEMENT & INITIATION | [20 empty] | Ongoing across full project lifecycle
1.1 | Kick-off Meeting & Requirements Review | ALL | 2 | W1 | W1 | [16 empty] | Spec sign-off; team role assignment | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W1
1.2 | Architecture & Tech Stack Decision | ALL | 3 | W1 | W1 | [16 empty] | WPF/.NET 8, Modbus TCP, FTP protocol confirmed | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W1
1.3 | Project Repository & CI Pipeline Setup | BE1 | 2 | W1 | W1 | [16 empty] | Git repo, branching strategy, build pipeline | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W1
1.4 | Sprint Planning & Weekly Stand-ups | [20 empty] | Daily stand-up; 2-week sprints
1.5 | Risk Register & Mitigation Plan | ALL | 2 | W1 | W1 | [16 empty] | Top risks: Keyence CCD API, PLC timing, FTP bandwidth | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W1
2 | DESIGN & ARCHITECTURE | [20 empty] | All design documents signed off by end W3
2.1 | PLC-IPC Communication Protocol Design | BE1 | 4 | W1 | W2 | [16 empty] | Modbus register map (DM10000~DM10500+); read/write cycles | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W1 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W2
2.2 | DM Address Map Specification | BE1 | 3 | W1 | W2 | [16 empty] | All 9 DM blocks mapped: System/Control/CycleTime/OEE/Alarm/I-O/Manual/Param/Prod | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W1 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W2
2.3 | Camera / CCD Interface Design | BE2 | 4 | W1 | W2 | [16 empty] | Keyence CCD – IPC signal protocol; FTP folder structure; image naming | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W1 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W2
2.4 | Database & File Storage Design | BE1 | 3 | W2 | W3 | [16 empty] | Production image archive, 2D code logs, OEE historical data | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W2 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W3
2.5 | UI / UX Wireframes (all screens) | FE | 5 | W1 | W3 | [16 empty] | 10 screens: System/Control/CycleTime/OEE/Alarm/IOmon/Manual/Param/Prod/Camera | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W1 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W3
2.6 | ★ Design Review & Sign-off | ALL | 1 | W3 | W3 | [16 empty] | Milestone: Design freeze | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W3
3 | BACKEND DEVELOPMENT – COMMUNICATION LAYER | [20 empty] | PLC↔IPC Modbus TCP + CCD↔IPC FTP
3.1 | PLC Communication Service (Modbus TCP) | BE1 | 5 | W4 | W5 | [16 empty] | Connect, heartbeat pulse (1s), polling loop (0.1s & 5s cycles) | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W4 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W5
3.1.1 | Heartbeat Signal (CD_COM_PULSE_PLC/IPC) | BE1 | 2 | W4 | W4 | [16 empty] | DM10000.0 / DM10015.0 – 1-sec toggle
3.1.2 | System Data Polling (Date/Time sync) | BE1 | 2 | W4 | W4 | [16 empty] | DM10004~DM10009 / DM10019~DM10024 – 5-sec poll
3.1.3 | Control Data Polling (Startup Conditions) | BE1 | 3 | W4 | W5 | [16 empty] | DM10050 – 12 startup condition bits, 0.1s poll | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W4 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W5
3.2 | Cycle Time Module | BE1 | 3 | W5 | W6 | [16 empty] | DM10100-104: 1-cycle complete signal + real cycle time word | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W5 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W6
3.3 | OEE Data Module | BE1 | 4 | W5 | W6 | [16 empty] | DM10150~: availability, performance, quality metrics | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W5 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W6
3.4 | Alarm Module (PLC→IPC) | BE1 | 3 | W6 | W7 | [16 empty] | DM10200~: alarm codes, active/history lists, acknowledge | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W6 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7
3.5 | I/O Monitor Module | BE2 | 3 | W6 | W7 | [16 empty] | DM10220~250: real-time I/O state display (bit-level) | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W6 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7
3.6 | Manual Operation Module | BE2 | 4 | W6 | W8 | [16 empty] | DM10270~: tray lift, conveyor fwd/rev/stop, X/Y-axis JOG (11 signals) | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W6 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W8
3.6.1 | Tray Lift Signals (up/down) | BE2 | 1 | W6 | W6 | [16 empty] | Manual A1/A2 – 1-bit IPC→PLC
3.6.2 | Conveyor Control (fwd/rev/stop/slow/fast) | BE2 | 2 | W6 | W7 | [16 empty] | Manual A5~A9 | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W6 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7
3.6.3 | X/Y Axis JOG (fwd/back) | BE2 | 2 | W7 | W8 | [16 empty] | Manual A10/A11 | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W8
3.7 | Parameter Module | BE2 | 5 | W7 | W9 | [16 empty] | DM10300~: servo params (JOG speed, coordinates, accel/decel), X/Y axes | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W9
3.7.1 | Servo Parameter Confirm Signal | BE2 | 1 | W7 | W7 | [16 empty] | Param A1 – bit trigger to PLC | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7
3.7.2 | X-axis Parameters (JOG, coords, vel) | BE2 | 2 | W7 | W8 | [16 empty] | Param A5/A8~A11 – DWORD words | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W8
3.7.3 | Y-axis Parameters | BE2 | 2 | W8 | W9 | [16 empty] | Mirror of X-axis – Param A12+ | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W8 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W9
3.8 | Production Data Module | BE1 | 5 | W7 | W9 | [16 empty] | DM10500~: 2D code (3×20-word strings), image trigger signals | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W9
3.8.1 | 2D Code Reception (Work1/2/3) | BE1 | 2 | W7 | W8 | [16 empty] | DM10500~DM10559 – String 20-Word × 3 | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W8
3.8.2 | Image Trigger & Data-Send Signals | BE1 | 2 | W8 | W9 | [16 empty] | Production send/receive bit triggers | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W8 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W9
3.9 | ★ BE Communication Layer Review | ALL | 1 | W9 | W9 | [16 empty] | Milestone: all PLC↔IPC tags verified against DM plan | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W9
4 | BACKEND DEVELOPMENT – CAMERA / CCD INTEGRATION | [20 empty] | Keyence CCD + FTP image pipeline
4.1 | Keyence CCD Signal Interface | BE2 | 4 | W4 | W5 | [16 empty] | Discuss signal spec with Keyence; trigger/ack handshake | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W4 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W5
4.2 | FTP Server Setup & Image Receive Service | BE2 | 3 | W5 | W6 | [16 empty] | Receive: 2D_RAW_IMG, PRE_BEND_RAW/PROC, POST_BEND1/2_RAW/PROC (7 image types) | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W5 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W6
4.3 | Image Storage & Naming Convention | BE2 | 2 | W6 | W7 | [16 empty] | Folder: /images/{date}/{workNo}/{type}.bmp; retention policy | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W6 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7
4.4 | IPC Ready Signal to PLC (after image save) | BE2 | 2 | W7 | W8 | [16 empty] | Once image saved and IPC ready, send ready bit to PLC | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W8
4.5 | AOI / 2D Code Data Pipeline | BE2 | 3 | W8 | W10 | [16 empty] | Parse 2D code string from CCD; store; link to production record | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W8 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W10
4.6 | ★ Camera Module Integration Test | BE2 | 2 | W9 | W10 | [16 empty] | Milestone: end-to-end FTP image receive + 2D decode verified | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W9 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W10
5 | FRONTEND DEVELOPMENT | [20 empty] | WPF .NET 8 UI – 10 screens
5.1 | Base Shell: MainWindow, Navigation, Login | FE | 4 | W4 | W5 | [16 empty] | Ribbon, side nav, user login, role-based access | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W4 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W5
5.2 | System Status Screen | FE | 3 | W5 | W6 | [16 empty] | Heartbeat indicator, PLC/IPC connection status, date-time sync | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W5 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W6
5.3 | Startup Condition Screen (Control) | FE | 3 | W6 | W7 | [16 empty] | 12 startup condition bits displayed + status indicator | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W6 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7
5.4 | Cycle Time Screen | FE | 2 | W7 | W8 | [16 empty] | Real cycle time display, trend chart, target vs actual | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W8
5.5 | OEE Dashboard | FE | 4 | W7 | W9 | [16 empty] | Availability / Performance / Quality gauges + history chart | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W7 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W9
5.6 | Alarm Screen | FE | 3 | W8 | W9 | [16 empty] | Active alarm list, history, acknowledge button | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W8 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W9
5.7 | I/O Monitor Screen | FE | 3 | W9 | W10 | [16 empty] | Bit-level I/O table, real-time update, colour coding ON/OFF | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W9 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W10
5.8 | Manual Operation Screen | FE | 4 | W9 | W11 | [16 empty] | Tray lift, conveyor, X/Y JOG buttons + interlock indicators | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W9 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W11
5.9 | Parameter Setting Screen | FE | 4 | W10 | W12 | [16 empty] | Servo params input: JOG speed, coords, accel/decel; confirm button | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W10 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W12
5.10 | Production / Image View Screen | FE | 5 | W10 | W13 | [16 empty] | 2D code display, image gallery (pre/post-bend), FTP status | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W10 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W13
5.11 | UI Polish, Responsive Layout & Theming | FE | 3 | W12 | W13 | [16 empty] | Consistent fonts, colours, animations, multi-resolution support | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W12 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W13
5.12 | ★ FE Internal Review | ALL | 1 | W13 | W13 | [16 empty] | Milestone: all 10 screens functionally complete | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W13
6 | INTEGRATION | [20 empty] | Connect BE modules to FE screens
6.1 | System & Control Screens Integration | BE1 | 3 | W10 | W11 | [16 empty] | Wire heartbeat, startup conditions to UI | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W10 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W11
6.2 | CycleTime & OEE Integration | BE1 | 3 | W11 | W12 | [16 empty] | Real-time data feed to FE charts | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W11 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W12
6.3 | Alarm & I/O Monitor Integration | BE1 | 3 | W11 | W12 | [16 empty] | Live alarm feed, I/O bit states to UI | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W11 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W12
6.4 | Manual & Parameter Integration | BE2 | 3 | W12 | W13 | [16 empty] | Button commands → PLC; parameter writes verified | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W12 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W13
6.5 | Camera / Production Screen Integration | BE2 | 3 | W12 | W13 | [16 empty] | FTP images displayed in UI; 2D code linked to production record | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W12 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W13
6.6 | ★ End-to-End Integration Smoke Test | ALL | 2 | W13 | W14 | [16 empty] | Milestone: full machine cycle simulated (start → bend → image save) | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W13 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W14
7 | QA & TESTING | [20 empty] | Parallel QA from W10; formal test W13-15
7.1 | Test Plan & Test Case Authoring | QA | 5 | W10 | W12 | [16 empty] | Test cases for all 9 functional modules + camera | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W10 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W12
7.2 | Unit & Module Testing | QA | 5 | W11 | W13 | [16 empty] | PLC comms, FTP, 2D code, OEE calculation, alarm logic | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W11 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W13
7.3 | Integration Testing | QA | 4 | W13 | W14 | [16 empty] | All UI↔BE flows; edge cases: disconnect, timeout, corrupt image | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W13 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W14
7.4 | Performance & Timing Testing | QA | 3 | W14 | W15 | [16 empty] | Verify 0.1s poll, 1s heartbeat, 5s date sync within tolerance | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W14 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W15
7.5 | UAT (User Acceptance Testing) with Customer | QA | 4 | W14 | W16 | [16 empty] | Customer sign-off on all functional requirements | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W14 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W16
7.6 | Bug Fix Cycle 1 | ALL | 5 | W14 | W15 | [16 empty] | Critical & high severity bugs fixed | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W14 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W15
7.7 | Bug Fix Cycle 2 / Regression | ALL | 3 | W15 | W16 | [16 empty] | Medium/low bugs + full regression suite | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W15 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W16
7.8 | ★ QA Sign-off | QA | 1 | W16 | W16 | [16 empty] | Milestone: zero critical bugs; QA certificate issued
8 | DEPLOYMENT & HANDOVER | [20 empty] | Production release & documentation
8.1 | Deployment Package Build & Installer | BE1 | 2 | W15 | W15 | [16 empty] | MSI installer, config files, version tag | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W15
8.2 | On-site Commissioning & PLC Live Test | BE1 | 3 | W15 | W16 | [16 empty] | Connect to actual PLC on Bending machine; verify all DM tags | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W15 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W16
8.3 | Camera Calibration & FTP Live Test | BE2 | 2 | W15 | W16 | [16 empty] | Keyence CCD live image capture verified on machine floor | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W15 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W16
8.4 | User Manual & Operator Guide | FE | 3 | W14 | W16 | [16 empty] | PDF manual with screenshots; alarm code table | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W14 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W16
8.5 | Technical Documentation & Code Handover | BE1 | 3 | W14 | W16 | [16 empty] | Architecture doc, DM map, API doc, Git access transferred | bar: Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W14 to Reference Spec: Bending_Flow_Tag (Specification for Adding a Camera) ¦ Modules: System · Control · CycleTime · OEE · Alarm · I/O Monitor · Manual · Parameter · Production · Camera/CCD W16
8.6 | ★ Project Closure & Final Handover | ALL | 1 | W16 | W16 | [16 empty] | Milestone: Customer acceptance sign-off ✓
TOTAL PROJECT DURATION |  |  | 16 Weeks

## Resource Summary
TEAM RESOURCE SUMMARY – BENDING MACHINE PROJECT
Role | Responsibilities | Active Weeks | Key Deliverables
BE1 (Backend Eng 1) | PLC Modbus TCP comm, System/Control/CycleTime/OEE/Alarm/Production modules, DB design, deployment | W1–W16 | PLC service, DM map, prod data module, deployment pkg
BE2 (Backend Eng 2) | Camera/CCD integration, FTP pipeline, I/O Monitor, Manual Op, Parameter modules, image storage | W1–W16 | CCD interface, FTP service, image pipeline, manual/param modules
FE (Frontend Eng) | WPF .NET 8 UI: all 10 screens, navigation, themes, operator manual | W1–W16 | 10 screens, user manual, UI component library
QA (Quality Assur.) | Test plan, module/integration/performance/UAT testing, bug triage, regression suite | W10–W16 | Test plan, 200+ test cases, QA cert, zero-critical sign-off