## WBS Project Plan
BENDING MACHINE IPC SOFTWARE — WBS PROJECT PLAN
Team: 2 BE (BE1=PLC/Data, BE2=Camera/Modules) · 1 FE · 1 QA ¦ Duration: 16 Weeks ¦ Bending Process: UAT#1,2 & UAT#3
WBS# | Task / Deliverable | Owner | Wks | Start | End | Dep | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
Legend: |  | ■ BE1 (PLC/Data) |  | ■ BE2 (Camera/Modules) |  |  | ■ FE (Frontend) |  |  | ■ QA |  |  | ■ PM / Shared |  |  | ■ ★ Milestone
1 | PROJECT MANAGEMENT | PM | 16 | W1 | W16 | -
1.1 | Kickoff & scope definition | PM | 1 | W1 | W1 | -
1.2 | Sprint planning & weekly stand-ups | PM | 14 | W2 | W15 | 1.1
1.3 | Risk register & change management | PM | 14 | W2 | W15 | 1.1
1.4 | ★ Project Kick-off Complete | PM | ★ | W1 | W1 | 1.1 | ★
2 | SYSTEM ARCHITECTURE & DESIGN | BE1 | 2 | W1 | W2 | -
2.1 | Bending machine IPC architecture design | BE1 | 2 | W1 | W2 | 1.1
2.2 | DM register address map review (DM10000~) | BE1 | 1 | W1 | W1 | 1.1
2.3 | PLC↔IPC data flow design (start/end/alarm) | BE1 | 1 | W2 | W2 | 2.2
2.4 | Camera FTP image pipeline architecture | BE2 | 1 | W2 | W2 | 2.1
2.5 | Database schema: production + quality data | BE1 | 1 | W2 | W2 | 2.1
2.6 | ★ Architecture Sign-off | PM | ★ | W2 | W2 | 2.5 |  | ★
3 | PLC COMMUNICATION LAYER | BE1 | 4 | W2 | W5 | -
3.1 | Modbus TCP connection manager (heartbeat DM10000~) | BE1 | 2 | W2 | W3 | 2.3
3.2 | Program start trigger / end trigger handler | BE1 | 1 | W3 | W3 | 3.1
3.3 | Alarm signal receive & dispatch (DM10200~) | BE1 | 1 | W3 | W3 | 3.1
3.4 | Date/time sync register (DM10010~) | BE1 | 1 | W4 | W4 | 3.1
3.5 | DM register read/write service (all DM blocks) | BE1 | 2 | W3 | W4 | 3.1
3.6 | Unit tests: Modbus read/write & error handling | QA | 1 | W5 | W5 | 3.5
3.7 | ★ PLC Comm Layer Verified | BE1 | ★ | W5 | W5 | 3.6 |  |  |  |  | ★
4 | IN-STOCK MODULE IPC | BE2 | 3 | W3 | W5 | -
4.1 | Tray loading into stocker — count tracking | BE2 | 1 | W3 | W3 | 3.1
4.2 | Flex pick-up from tray — inflow count (DM10500~) | BE2 | 1 | W3 | W3 | 4.1
4.3 | Put-in bending jig — location confirmation | BE2 | 1 | W4 | W4 | 4.2
4.4 | Miss set-material detection / Discharge Toss | BE2 | 1 | W4 | W4 | 4.3
4.5 | Empty tray discharge event handling | BE2 | 1 | W5 | W5 | 4.4
5 | BENDING MODULE IPC (UAT#1,2 & UAT#3) | BE1 | 4 | W4 | W7 | -
5.1 | UAT#1,2 process state machine (Clamp→Punch→Heat→Hold→Unclamp) | BE1 | 2 | W4 | W5 | 3.5
5.2 | UAT#3 process state machine (Clamp→Punch→Heat→Hold→Unclamp) | BE1 | 2 | W5 | W6 | 5.1
5.3 | Actual load at bending — data collection & store | BE1 | 1 | W5 | W5 | 5.1
5.4 | Actual temperature at bending — data collect (80°C target) | BE1 | 1 | W5 | W5 | 5.1
5.5 | Tossed-before-bending count (DM10100~ cycle time) | BE1 | 1 | W6 | W6 | 5.2
5.6 | Bending parameter write to PLC (DM10300~ servo) | BE1 | 1 | W6 | W6 | 5.2
5.7 | ★ Bending Module IPC Complete | BE1 | ★ | W7 | W7 | 5.6 | [6 empty] | ★
6 | CAMERA / VISION INTEGRATION (Keyence CCD) | BE2 | 5 | W4 | W8 | -
6.1 | Keyence CCD SDK integration & connection | BE2 | 1 | W4 | W4 | 2.4
6.2 | Pre-bend image capture — Flat Flex (before bend) | BE2 | 2 | W5 | W6 | 6.1
6.3 | Post-bend image capture — 3-side inspection | BE2 | 2 | W6 | W7 | 6.2
6.4 | FTP image transfer pipeline (IPC→server) | BE2 | 1 | W7 | W7 | 6.3
6.5 | Dimension measurement result receive & store | BE2 | 2 | W7 | W8 | 6.3
6.6 | NG determination logic (dim threshold check) | BE1 | 1 | W8 | W8 | 6.5
6.7 | ★ Camera Integration Verified | BE2 | ★ | W8 | W8 | 6.6 | [7 empty] | ★
7 | REMOVE LINER & VISION INSPECT MODULE IPC | BE2 | 3 | W7 | W9 | -
7.1 | Move flex after bending — state tracking | BE2 | 1 | W7 | W7 | 5.7
7.2 | Liner removal confirmation + Discharge Film | BE2 | 1 | W8 | W8 | 7.1
7.3 | Turn part — Move flex to inspection position | BE2 | 1 | W8 | W8 | 7.2
7.4 | Inspection Flex result (OK/NG) from vision | BE2 | 1 | W9 | W9 | 7.3
7.5 | NG-Toss discharge event (Discharge NG-Toss 9') | BE2 | 1 | W9 | W9 | 7.4
8 | OUT-STOCK MODULE IPC | BE2 | 2 | W9 | W10 | -
8.1 | Flex aligned on pallet — positioning confirm | BE2 | 1 | W9 | W9 | 7.5
8.2 | Packed-out pallets with parts — count tracking | BE2 | 1 | W10 | W10 | 8.1
8.3 | Empty pallet supply event | BE2 | 1 | W10 | W10 | 8.1
8.4 | OK count (DM10150~ OEE) / NG count finalization | BE1 | 1 | W10 | W10 | 8.2
9 | PRODUCTION DATA, OEE & MANUAL OPERATION | BE1 | 3 | W8 | W10 | -
9.1 | OEE calculation engine (DM10150~: avail/perf/qual) | BE1 | 2 | W8 | W9 | 5.7
9.2 | Cycle time data logging (DM10100~) | BE1 | 1 | W9 | W9 | 9.1
9.3 | Manual operation mode (DM10270~: tray/conveyor/JOG) | BE1 | 2 | W9 | W10 | 3.5
9.4 | Startup conditions check — 12 conditions (DM10050~) | BE1 | 1 | W10 | W10 | 9.3
9.5 | Output to CM server / PDCA cloud (network export) | BE1 | 1 | W10 | W10 | 9.1
10 | FRONTEND DEVELOPMENT | FE | 7 | W5 | W11 | -
10.1 | Main dashboard — Production info (green) + Quality info (blue) | FE | 3 | W5 | W7 | 3.7
10.2 | Bending process flow visualizer (10-step line flow) | FE | 2 | W6 | W7 | 10.1
10.3 | UAT#1,2 & UAT#3 real-time status panel | FE | 2 | W7 | W8 | 10.2
10.4 | Camera image viewer — pre-bend flat flex | FE | 2 | W7 | W8 | 6.7
10.5 | Camera image viewer — post-bend 3-side viewer | FE | 2 | W8 | W9 | 10.4
10.6 | Alarm & NG management screen (DM10200~) | FE | 2 | W8 | W9 | 10.1
10.7 | OEE & production statistics charts | FE | 2 | W9 | W10 | 9.1
10.8 | Manual operation UI panel (tray/conveyor/JOG) | FE | 1 | W10 | W10 | 9.3
10.9 | Startup condition check screen (12 conditions) | FE | 1 | W10 | W10 | 9.4
10.10 | ★ Frontend Modules Complete | FE | ★ | W11 | W11 | 10.9 | [10 empty] | ★
11 | INTEGRATION TESTING | QA | 3 | W11 | W13 | -
11.1 | PLC↔IPC end-to-end test (all DM registers) | QA | 1 | W11 | W11 | 3.7
11.2 | Bending cycle full integration test (UAT#1,2,3) | QA | 1 | W11 | W11 | 5.7
11.3 | Camera pipeline integration — FTP + images | QA | 1 | W12 | W12 | 6.7
11.4 | Frontend ↔ backend data binding validation | QA | 1 | W12 | W12 | 10.10
11.5 | NG detection & toss flow end-to-end | QA | 1 | W12 | W12 | 11.2
11.6 | ★ Integration Test Pass | QA | ★ | W13 | W13 | 11.5 | [12 empty] | ★
12 | QUALITY ASSURANCE & UAT | QA | 2 | W13 | W14 | -
12.1 | Test case documentation for all 10 process steps | QA | 1 | W13 | W13 | 11.6
12.2 | Regression testing — bending load/temp accuracy | QA | 1 | W13 | W13 | 11.6
12.3 | UAT with site team on actual machine | QA | 1 | W14 | W14 | 12.1
12.4 | Bug fixes from UAT | BE1 | 1 | W14 | W14 | 12.3
12.5 | ★ UAT Sign-off | PM | ★ | W14 | W14 | 12.4 | [13 empty] | ★
13 | DEPLOYMENT & HANDOVER | BE1 | 2 | W15 | W16 | -
13.1 | IPC software deployment to site machine | BE1 | 1 | W15 | W15 | 12.5
13.2 | Production monitoring — first live bending run | BE1 | 1 | W15 | W15 | 13.1
13.3 | Technical documentation & operator manual | BE2 | 1 | W15 | W15 | 13.1
13.4 | Final handover & knowledge transfer | PM | 1 | W16 | W16 | 13.3
13.5 | ★ PROJECT COMPLETE | PM | ★ | W16 | W16 | 13.4 | [15 empty] | ★

## Resource Summary
RESOURCE SUMMARY — BENDING MACHINE IPC
Engineer | Role | Primary Responsibilities | Phases (WBS) | Active Weeks
BE1 | Backend Eng. 1 | PLC/Modbus comm, DM registers, Bending module (UAT#1,2,3), Load/Temp data, OEE, Manual op, Network export | 2,3,5,8(part),9,11(part),12(part),13 | W1–W16
BE2 | Backend Eng. 2 | Keyence CCD camera, FTP pipeline, In-Stock/Remove Liner/Out-Stock modules, Vision inspect | 2(part),4,6,7,8,10(part),13(part) | W1–W15
FE | Frontend Eng. | Dashboard (prod+quality), 10-step flow visualizer, UAT status panels, image viewers (pre/post bend), alarms, OEE charts | 10 | W5–W11
QA | QA Engineer | Unit tests (PLC), integration tests (all modules), UAT (on-site machine), regression, bending cycle validation | 3(part),11,12 | W5–W15
PM | Project Manager | Kickoff, sprint planning, risk management, change control, UAT sign-off, final handover | 1,2(part),13(part) | W1–W16
BENDING MACHINE — 10-STEP PROCESS FLOW (Reference)
Step | Process Action | Module | Owner | IPC Data / Event
Step 1 | Pick-up Part from tray | In-Stock Module | BE2 | Number of inflow
Step 2 | Inspection (Miss set-Material check) | In-Stock Module | BE2 | Discharge Toss at 2'
Step 3 | Put in Bending jig | In-Stock Module | BE2 | Location Confirmation
Step 4 | Bending process — UAT#1,2 (Clamp→80°C→10s→Unclamp) | Bending Module | BE1 | Load + Temp data
Step 5 | Bending process — UAT#3 (Clamp→80°C→10s→Unclamp) | Bending Module | BE1 | Tossed before bend
Step 6 | Move Part | Remove Liner Module | BE2 | -
Step 7 | Remove Liner | Remove Liner Module | BE2 | Discharge Film
Step 8 | Turn Part | Vision Inspect Mod. | BE2 | -
Step 9 | Inspection Flex (Dimension measure) | Vision Inspect Mod. | BE2 | Image 3-side + NG-Toss 9'
Step 10 | Part aligned on pallet → Packed out | Out-Stock Module | BE2 | Number of OK/NG