## BendingCodeDocs
Bending Issues
Sno | Problem Statement
1 | In order to create new EventSource name , the Application/Visual Studio should run with Administrator previlages.
2 | For Background Core Service , user have to register Core Service as a "Window Service" as the following steps.
Open the Cmd Promt using Admin Rights and enter the following query-
sc create "ServiceName" binpath="Path where Service .exe exist" start=auto sc start "ServiceName" sc query "ServiceName" >>>>>>>>>>>>>>>>>>>>>>>>>> In case to delete Registered Service- sc delete "ServiceName"
Tip - : Use ServiceName "IPCSoftware.CoreService.Bending" for Bending Service , "IPCSoftware.CoreService.AOI" for AOI service.

## Remove HardCode Data
Start Date- 13/05/2026 |  | Complete Date -
Tightly couple binding - UI - CoreService
Sno | NameScape | FileName | MethodUsed | Line No. | Item | Depedency File
1 | IPCSoftware.App.ViewModels | OEEDashboardViewModel | ToggleMacMini() | 485-486 | IsMacMiniEnabled | appSettings.json
2 | IPCSoftware.App.ViewModels | AeLimitViewModel | SaveAndTransferAsync() | 146-151 | InspectionXUnit, InspectionYUnit, InspectionAngleUnit | appSettings.json
3 | IPCSoftware.UI.CommonViews.ViewModels | AeLimitViewModel | SaveAndTransferAsync() | 143-148 | InspectionXUnit, InspectionYUnit, InspectionAngleUnit | appSettings.json
4 | IPCSoftware.UI.CommonViews.ViewModels | ApiTestViewModel | SaveSettings() | 205-209 | Protocol, MacMiniIpAddress, Port, EndPoint, PreviousMachineCode, AOIMachineCode | appSettings.json
Present dependency pattern
Proposed
💡 Proposed Solution Pattern
Replace file writes with TCP Request/Response:
// Instead of:
File.WriteAllText(appSettingsPath, jsonObj.ToString());
// Use:
await _coreClient.WriteSettingAsync("External.IsMacMiniEnabled", newValue);
UI LAYER VIEW MODEL
appSettings.json
Core Service (Background)
IOption<T> (Reload Delay)
File.WriteAllText
UI LAYER VIEW MODEL
Core Service (Background)
Response PAckage (new ID 9)
Request Package

## Code_Optimize
Code Optimization Work |  |  | Working Branch- Pending-Task-Rishabh
Sno | Task | Remark | Reported Date | Completed Date | Status | Remarks
1 | DeviceConfigurationService.cs-:To Rename GetPLCDeviceAsync() function with GetDeviceInterfaceAsync() | The previous function name misleading in order by name in class structure. | 17/04/2026 | 17/04/2026 | Done
2 | Create DeviceInterfaceConfigLoader Class | Extracted CSV loading logic for Device Interfaces into dedicated loader class for separation of concerns. | 17/04/2026 |  | Done
2a | Refactor LoadInterfacesFromCsvAsync() Method | Modified to use DeviceConfigLoader.Load() instead of inline parsing logic.
2b | Inject DeviceInterfaceConfigLoader & CameraConfigLoader in Constructor | Updated DeviceConfigurationService constructor to accept loaders via dependency injection.
2c | Register DeviceConfigLoader in DI Container | Added ServiceRegistration.cs & Program.cs registrations (Singleton) for both loaders.
3 | Correct Indentation | Proper indentation makes code easy to read, understand, and prevents logical errors. | 17/04/2026 |  | In Progress | (4/297)Files = 1.34%
4 | Save Function () removal from DeviceConfigurationService.cs | Add SaveCsv() functions in - DeviceInterfaceConfigLoader -CameraConfigLoader -DeviceConfigLoader | 17/04/2026 | 19/04/2026 | Done
5 | Parse/Split/Escape Function () removal from DeviceConfigurationService.cs | Add Parse/Split/Escape Function () in - DeviceInterfaceConfigLoader -CameraConfigLoader -DeviceConfigLoader | 17/04/2026 | 19/04/2026 | Done
6 | Create GetHeader() function in CsvReader class | This function will get header line of csv files which will later implement in SaveCsv() function | 17/04/2026 | 18/04/2026 | Done
7 | Ceate new class DeviceLoader() | Extracted CSV loading logic for Devices into dedicated loader class for separation of concerns. | 17/04/2026 | 18/04/2026 | Done
8 | CsvReader name change | CsvReader.cs class should remaned to CsvManager.cs | 24/04/2026 | 25/04/2026 | Done
9 | CsvManager Inheritance | CsvReader now Inherit from new Interface Class IFileHandler contains all Csv function methods | 24/04/2026 | 25/04/2026 | Done
10 | Csv Manager Add On function
|  | write() | 24/04/2026 | 25/04/2026 | Done
11 | Save() function in TagConfigLoader class | Save() function should implement in TagLoader instead PLCTagConfigService | 24/04/2026 | 27/04/2026 | Done
12 | Optimization of PLCTagConfigurationService | TagConfigLoader now implement in DeviceConfiguationService | 23/04/2026 |  | Done
| DeviceConfigurationService |  |  |  | Done
AppLogger
LogManager
13 | Correction - | _tagService Field create confusion now as it was replaced by Device so the Field name should be _deviceService | 28-04-2026 | 28-04-2026 | Done
14 | Correction - | the name Csv in PathName create confusion ,as the loader ref changed to multiple posible extension. Change name toConfigPath | 28-04-2026 | 28-04-2026 | Done
15 | Duplication of initialize service | App.xaml.cs and AppInitializationService | 28-04-2026 | 28-04-2026 | Done

## DeviceConfig-Optimize
OLD
Device.csv
DeviceInterface.csv
CameraInetrface.csv
PLCTag.csv
Update date - 24-04-2026
Device.csv
DeviceInterface.csv
CameraInetrface.csv
PLCTag.csv
Update date- 27-04-2026 (Factory Method)
Device.csv
DeviceInterface.csv
CameraInetrface.csv
PLCTag.csv
GetHeader() ,GetVersion(),Write(),EScape()
DeviceConfigLoader
DeviceInterfaceConfigLoader
CameraConfigLoader
TagConfigLoader
CsvrEADER{ Load() /Save() etc}
DEviceConfigurationSErvice
PLCTagConfigurationService
DeviceConfigLoader
DeviceInterfaceConfigLoader
CameraConfigLoader
TagConfigLoader
CsvManager{ Load() /Save() etc}
DEviceConfigurationSErvice
PLCTagConfigurationService
IFileHandler{Load() ,/Save()}
CsvManager{ Load() /Save() etc}
DeviceConfigLoader
DeviceInterfaceConfigLoader
CameraConfigLoader
TagConfigLoader
DEviceConfigurationSErvice
PLCTagConfigurationService
IFileHandler{Load() ,/Save()}
ConfigLoaderService
All Methods Transfered
Deleted-28-04-26
Added New Class-27-04-26

## TraceLog CallRef
TRACE LOG FILE -CALL REF | Last Update -27-04-26
|  |  | Methods() | Resposibility
|  |  | WriteCsv() | To Write values in dedicated csv file
|  |  | ResolveLogFile() | It determines the target log file path by formatting date-stamped filenames
Contructor Calling
To Append All Text in FilePath
LogManagerService
ResolveLogFile()
AlgorithmAnalysisService
Apply(plcno ,value)
CsvManager :IFileHandler
WriteCsv()
New Method()
OldMethod()
Class {}
DashboardInitializer
StartAsync()
LogTrace(message)
AppLoggerService
WriteToFileSafe(LogEntry)
Return FilePath for TrcaLog
DeviceConfigurationService
Return _tags from GetAllTagsAsync()
Logic to Filter EnableTrace tags

## ErrorLogging-Struct
Data Flow Sequence Diagram